## Sheet1
features | user stories | Sprint | Priority | Estimation per story points | Assignment
Create account | As a first time user, I want to create account so that i can use the app | 1 | High | 4 | Ahmed
view restaurants | As a user, i want to view restaurants so that i can choose the one where I will order from | 1 | Medium | 8 | Michel
search restaurants | As a user, I want to search restaurants so that i can find the nearst retaurant to me | 1 | Medium | 10 | Mariam
| As a user, I want to search restaurants so that i can find the type of food I want to eat | 2 | High | 12 | Reda
| As a restaurant, I want to search restaurants so that i can find the type of food I want to eat | 2 | Low | 3 | Ali
View menu | As a user, i want to view menu of restaurants so that i can choose The food I want to eat | 2 | Low | 4 | Ahmed
Add to cart | As a user, i want to add food to cart so that i can review the final order before confirming the order | 2 | High | 9 | Michel
Purchase | As a user, I want to purchase so that i can choose the payment method I want | 3 | High | 4 | Mariam
Restaurant views order | As a user, I want to view restaurants by different orders so that I can choose the cheapest restaurant of chinese food | 4 | Low | 2 | Reda
Restaurant mark order as delivered | As a user, I want to view the delivered orders so that I can repeat orders easily | 4 | Low | 4 | Ali
| As a user, I want to view the delivered orders so that I can calculate my budget spent on food | 4 | Low | 7 | Ahmed