## Sheet1
| Activity Task | Task | Subtask | Number of hours | Hour price ($) | Estimated cost
1 | Plan |  |  | 24 |  | 320
| 1.1 | Create Stakeholders Enagement Plan |  | 4 | 20 | 80
| 1.2 | Create Stakeholder Communication Plan |  | 4 | 20 | 80
| 1.3 | Create Team Charter |  | 16 | 10 | 160
2 | Design |  |  | 80 |  | 4720
| 2.1 | Create Software Archictecture |  | 40 | 50 | 2000
| 2.2 | Review Software Archictecture |  | 24 | 80 | 1920
| 2.3 | Rework Software Archictecture |  | 16 | 50 | 800
3 | Implement |  |  | 2400 |  | 36000
| 3.1 | Develop Mobile App to be used by purchaser |  | 1600 | 15 | 24000
| 3.2 | Develop application to be used by shops |  | 400 | 15 | 6000
| 3.3 | Develop application Io be used by Customer |  | 400 | 15 | 6000
4 | Test |  |  | 960 |  | 13440
| 4.1 | Test Mobile App to be used by purchaser |  | 640 | 14 | 8960
| 4.2 | Test application to be used by shops |  | 160 | 14 | 2240
| 4.3 | Test application to be used by Customer |  | 160 | 14 | 2240
5 | Deploy |  |  | 1064 |  | 16080
| 5.1 | Take approval from customer |  | 24 | 20 | 480
| 5.2 | Deploy with small number of shops |  | 200 | 15 | 3000
| 5.3 | Rework based on feedback |  | 40 | 15 | 600
| 5.4 | Full deployment |  | 800 | 15 | 12000
6 | Closure |  |  | 48 |  | 960
| 6.1 | Document list of open issues |  | 16 | 20 | 320
| 6.2 | Document list of leasons learned |  | 16 | 20 | 320
| 6.3 | Team appraisal |  | 16 | 20 | 320
| SUM |  |  | 4576 |  | 71520
7 | Tools |  |  | 19 |  | 10500
| 7.1 | Design Tools |  | 4 | 1250 | 5000
| 7.2 | Implementation tools |  | 10 | 400 | 4000
| 7.3 | testing tools |  | 5 | 300 | 1500
| Overall cost |  |  | 4595 |  | 82020
| ESTIMATION ASSUMPTIONS |  |  | 29 |  | 14500
| 1 | HR Team hire the project team according to the¦ communicated schedule
| 2 | Customer submits the full requirements 9-Feb-2023
| 3 | Supplier delivers the required tools on 13-May-2023