## Sheet1
working hours
user stories | Estimation per hour | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12
As a first time user, I want to create account so that i can use the app | 20 | 10 | 10
As a user, i want to view restaurants so that i can choose the one where I will order from | 30 |  |  | 10 | 10 |  | 10
As a user, I want to search restaurants so that i can find the nearst retaurant to me | 60 | 10 |  |  |  | 20 |  |  |  |  | 30
As a user, I want to search restaurants so that i can find the type of food I want to eat | 120 | [6 empty] | 50 | 40 | 30
As a restaurant, I want to search restaurants so that i can find the type of food I want to eat | 40 |  | 20 | 20
As a user, i want to view menu of restaurants so that i can choose The food I want to eat | 80 |  |  |  | 40 |  | 30 |  |  |  |  | 10
As a user, i want to add food to cart so that i can review the final order before confirming the order | 50 |  | 20 | 10 |  | 20
As a user, I want to purchase so that i can choose the payment method I want | 20 | [8 empty] | 10 |  |  | 10
As a user, I want to view restaurants by different orders so that I can choose the cheapest restaurant of chinese food | 90 |  |  | 30 |  |  | 20 |  |  |  | 20 | 20
As a user, I want to view the delivered orders so that I can repeat orders easily | 100 |  | 30 |  |  | 40 |  |  | 20 |  |  |  | 10
As a user, I want to view the delivered orders so that I can calculate my budget spent on food | 140 | 10 |  |  | 30 |  |  | 30 |  | 30 |  | 40
Total working hours |  | 30 | 80 | 70 | 80 | 80 | 60 | 80 | 60 | 70 | 50 | 70 | 20
Total actual remaining working hours | 750 | 720 | 640 | 570 | 490 | 410 | 350 | 270 | 210 | 140 | 90 | 20 | 0
Total expected remaining working hours | 750 | 685 | 620 | 555 | 490 | 425 | 360 | 295 | 230 | 165 | 100 | 35 | 0